## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Owner & CEO | H | M | Has ultimate power as owner & CEO but busy with many responsibilities.
Deanna Coleman | Director of Operations | H | H | Leads daily communication and operations, very involved in project success.
Carter Ward | Executive Chef | M | H | Final say on menu choices, influential but less power over other areas
Gilly Tyson | General Manager (North) | M | M | Manages North location, operational role, direct contact with staff/customers.
Alex Schmidt | General Manager (Downtown) | M | M | New to restaurant management but responsible for Downtown location operations.
Nia Williams | General Manager (Waterfront) | M | M | Experienced, passionate about success, manages Waterfront location.
Zane Dutchman | Kitchen Manager (North) | L | M | Oversees back of house operations but learning and junior in role.
Larissa Stein | Kitchen Manager (Downtown) | L | M | Experienced but new to this restaurant, oversees Downtown kitchen operations.
Seydou Diallo | Restaurant Technology Consultant | L | L | External consultant, first major project, interested but limited power or influence.
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront